## labour+material (Mulund) (hidden)
OBEROI CONSTRUCTIONS LIMITED
Project : | Eternia
VENDOR EVALUATION FORM
NAME OF CONTRACTOR : Teamone HVAC Services Pvt. Ltd. |  |  | Bill no -RA 02
WORK ORDER NO :- 4610008036 |  |  | BILLING PERIOD :- Upto April 2021
WORK DESCRIPATION :- SITC of HVAC System -Clubhouse
SR. No. | Evaluation Criteria | OCL Rating | Remarks
A. | QUALITY
1 | Quality of Work
2 | Skill of Manpower / Workmanship
3 | Prompt Rectification
4 | Wastage Norms Adherence
5 | Adequacy of Plants & Machinery
B. | PROGRESS
6 | Preparation of Schedule
7 | Following the Schedule
8 | Adequacy of Manpower
C. | BEHAVIOR
9 | Co-operation, Communication & Co-ordination
10 | Housekeeping
11 | Change Management
12 | Dispute Resolution
D. | COMPLIANCES
13 | Statutory Compliances
14 | Financial Compliances
15 | Emergency & Safety Compliances
Scale: Poor <, :3 / Average : 4 – 5 / Satisfactory : 6 / Good : 7 / Very Good : 8 / Excellent : 9 - 10
Note :-Below 4 rating justification remark compulsory
Kaustubh Burange
SITE ENGG / SECTION INCHARGE |  |  | Project Incharge

## Checklist (hidden)
|  | PROJECT | : ETERNIA |  |  | W. O. No. |  |  | : 4610008036
|  | VENDOR | : TEAMONE HVAC SERVICES PVT. LTD. |  |  | W. O. Date |  |  | : 30/11/2020
|  | Invoice Date | :16/06/2021 |  |  | Scope of Work |  |  | : SITC of HVAC Works at Clubhouse, Eternia
|  | Invoice No. | : HVAC/2021-22/066 |  |  | RA Bill No. |  |  | : 02
[6 empty] | Billing Period |  |  | : Upto April 2021
CHECKLIST FOR WO INVOICES
|  |  |  | To be checked by* |  | YES | NO | Not Applicable |  | Comment
SITE CHECKLIST
> | MEASUREMENT
| - Approved Master Measurement Sheet |  |  |  | S |  | ü
| - Measurement Certification Status Log / Vector Sheet |  |  |  | S | ü |  |  |  | ………………
| - Vendor Measurement Sheet / Abstract Sheet |  |  |  | S | ü |  |  |  | ………………
| - Reconciliation Statement |  |  |  | S |  |  | ü |  | ………………
| - Material Escalation Statement with backups |  |  |  | S |  |  | ü |  | ………………
| - Debit / Credit Notes |  |  |  | S |  | ü |  |  | ………………
| - Debit / Credit Register |  |  |  | S |  | ü |  |  | ………………
> | ENCLOSURES
| - Delivery Challans / GRN |  |  |  | S |  |  | ü |  | ………………
| - Test reports |  |  |  | S |  |  | ü |  | ………………
| - Pour Card Summary |  |  |  | S |  |  | ü
| - QA reports |  |  |  | S |  |  | ü |  | ………………
| - Safety report |  |  |  | S |  |  | ü |  | ………………
| - Price Escalation statement / Break up |  |  |  | S |  | ü |  |  | ………………
| - NC Annexure attached |  |  |  | S |  | ü |  |  | ………………
> | STATUTORY TAXATION INFO
| - GST No. |  |  |  | S | ü |  |  |  | ………………
| - PAN No. |  |  |  | S | ü |  |  |  | ………………
| - HSN/SAC Code |  |  |  | S | ü |  |  |  | ………………
| - Any Other (Pl specify …………………………) |  |  |  | S |  |  | ü |  | ………………
> | COMPLIANCES
| - Compliance checklist, as verified by HO Compliance team, attached? |  |  |  | S | ü |  |  |  | ………………
| - Does the Compliance checklist match with the Billing Period? |  |  |  | S | ü |  |  |  | ………………
| - Compliance Stamp |  |  |  | S | ü
> | MISCELLANEOUS
| - Does the work done period on the submitted measurement sheet match with the period of measurement mentioned on the invoice? |  |  |  | S | ü |  |  |  | ………………
| - Invoice as per provision amount |  |  |  | S | ü
| - Is the tax component in vendor's bill in line with the regulations currently in force? |  |  |  | S | ü |  |  |  | ………………
| - Vendor's bill invoice value satisfies "Minmum Bill amount" stipulated in the W.O |  |  |  | S |  |  | ü |  | ………………
| - PBG: Amount……………. (Expiry Date: …... ) |  |  |  | S |  | ü |  | Equivalent Amount kept on held in RA01
| - ABG: Amount…Rs ....…..…... (Expiry Date:….......) |  |  |  | S |  |  | ü |  | ………………
| - RBG: Amount………….. (Expiry Date: ……….) |  |  |  | S |  |  | ü |  | ………………
> | SUBMISSIONS FOR FINAL BILL
| - No Dues certificate |  |  |  | S |  |  |  |  | ………………
| - Warranty Certificate |  |  |  | S |  |  |  |  | ………………
| - DLP Guarantee Certificate |  |  |  | S |  |  |  |  | ………………
| - Testing & Commissioning Certificate |  |  |  | S |  |  |  |  | ………………
| - As Built Drawings |  |  |  | S |  |  |  |  | ………………
| - Handing over documents as per WO |  |  |  | S |  |  |  |  | ………………
| - Attic Stock Statement |  |  |  | S |  |  |  |  | ………………
| - Project-wide final consolidated Reconciliation Statement |  |  |  | S |  |  |  |  | ………………
| - Debit/Credit Notes Register |  |  |  | S |  |  |  |  | ………………
*Prepared by: Site Billing Engg./Manager - Gokarna Basnet Signature: …………....………….... Date: …………....
*Checked by: Project Manager - Kaustubh Burange Signature: …………....………….... Date: …………....
*Approved by: Construction Head- Signature: …………....………….... Date: …………....
HO CHECKLIST
˃ | Are Vendor's counter-guarantees / IB in force and adjusted on COP generation date?
| - PBG (Expiry Date: …………………………) |  |  |  | HO |  |  |  |  | ………………
| - Mobilisation Advance (ABG Expiry Date: …………………………) |  |  |  | HO |  |  |  |  | ………………
| - Retention BG |  |  |  | HO |  |  |  |  | ………………
| - Shuttering Advance |  |  |  | HO |  |  |  |  | ………………
| - Other Advances (Pl specify:…………………………) (Due Date:…………………) |  |  |  | HO |  |  |  |  | ………………
˃ | Are Vendor's Insurance Policies in force? (CAR, WC, ...) |  |  |  | HO |  |  |  |  | ………………
> | Bank Statement of dedicated bank (Last three months) |  |  |  | HO
˃ | Recoveries made in this COP
| - Advance Payment |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Mobilisation Advance |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Material Advance |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Shuttering Advance |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Other Advance |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Retention |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Progressive Retention in lieu of PBG |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Amount(s) retained, if any |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
| - Liquidated damages / delay penalties |  | - Recovered in this bill |  | HO |  |  |  |  | ………………
*Prepared by: HO Billing Engg./Manager …………....…………....………….... Signature: …………....………….... Date: …………....
*Checked by: HO Billing In-charge …………....…………....………….... Signature: …………....………….... Date: …………....
ACCOUNTS CHECKLIST
| - Disallowed MVAT |  |  |  | A |  |  |  |  | ………………
| - Vendor Balance Confirmation |  |  |  | A |  |  |  |  | ………………
| - 407-408 statement |  |  |  | A |  |  |  |  | ………………
| - GST Mismatch |  |  |  | A |  |  |  |  | ………………
| - Expired BG of any other projects |  |  |  | A |  |  |  |  | ………………
| - Provision given for old period |  |  |  | A |  |  |  |  | ………………
| - PBG in place for the first RA bill |  |  |  | A
*Checked by: Accounts Payable team …………....…………....………….... Signature: …………....………….... Date: …………....
FORMAT: 05.09.2019 (Rev 3)

## Invoice (hidden)
PROFORMA INVOICE
Original for Recipient
Contractor Details: |  |  |  | Details of Receiver (Billed to)
Name |  | TEAMONE HVAC SERVICES PVT. LTD. |  | Name: M/s Oberoi Constructions Ltd.
Address |  | Office No. 306, Jhalawar Building, Patanwala Compound, Opp. Shreyas Cinema, Ghatkopar west, Mumbai - 400086 |  | Address: Commerz, 3rd Floor, International Business Park, Oberoi Garden City, Off Western Express Highway, Goregaon(E), Mumbai- 400063
GSTIN No. |  | 27AADCT2310C1ZX |  | GSTIN/Unique ID: 27AAACO1805E1ZX
PAN No. |  | AADCT2310C |  | PAN NO : AAACO1805E
Invoice No. |  | THS/21-22/004-OCL |  | State: Mahatashtra
Date of Invoice |  | 2021-05-10 |  | State Code: 27
W.O. No. |  | W.O.No. 4610008036, Dated: 30.11.2020
Reverse Charge:(Yes/No) |  | No
Details of Consignee (Shipped to)
Adderss: Oberoi Constructions Ltd, Mulund , Mumbai.
Project: Supply & Installation of Clubhouse HVAC Work at Eternia at LBS Road, Near Johnson & Johnson, Mulund West, Mumbai - 400 080
State: Maharashtra
State Code: 27
GSTIN / Unique ID: 27AAACO1805E1ZX
Place of Supply: Mumbai, Maharashtra
Sr. No. | Description |  | Previous Bill Amount INR | This Bill Amount INR | Cumulative Bill Amount INR
SAC CODE : 9954
A | Hi-Side Supply of VRV System |  | 0 | #REF! | #REF!
B | Hi-Side Installation of VRV System |  |  | #REF! | #REF!
C | Low-Side Supply & Installation of VRV System |  |  | #REF! | #REF!
| Total : |  | 0 | #REF! | #REF!
D | Add Taxes
i | CGST - (@14%) on [(A)] |  | 0 | #REF! | #REF!
ii | SGST - (@14%) on [(A)] |  | 0 | #REF! | #REF!
iii | CGST - (@9%) on [(B)] |  | 0 | #REF! | #REF!
iv | SGST - (@9%) on [(B)] |  | 0 | #REF! | #REF!
(D) | Total : [D.i + D.ii + D,iii + D,iv] |  | 0 | #REF! | #REF!
E | Gross Work Done Amount Including Taxes [A+B+C+(D)] |  | 0 | #REF! | #REF!
F | Recoveries (if any)
i
ii
(F) | Total Deductions |  | 0 | 0 | 0
G | NET PAYABLE AMOUNT [E - (F)] |  | 0 | #REF! | #REF!
NET PAYABLE AMOUNT IN WORDS (INR) :- |  |  | #NAME?
(Name, Designation & Signature of Authirised Person)

## Abstract Sheet
OBEROI CONSTRUCTION PVT. LTD.
Site:- Eternia, Mulund | [9 empty] | Bill Period : upto
Name of Contractor: Falcon | [9 empty] | R.A. Bill No. : 01
Work Order No: 4610008602
ABSTRACT SHEET
BOQ No. | Item Description | Unit | Qty | Rate | Amount | QTY CERTIFIED |  |  | BILLED AMOUNT |  |  | % COMPL
[6 empty] | Previous | Present | Cum. | Previous | Present | Cum.
10 | Fire sealant filling in MCA area for TA
a) | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 | 90.18 | 51943.68 | 0 | 37.05 | 37.05 | 0 | 3341.169 | 3341.169 | 6.432%
b) | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 | 85.43 | 5467.52 | 0 | 7.6 | 7.6 | 0 | 649.268 | 649.268 | 11.88%
c) | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 | 142.38 | 36449.28 | 0 | 30.4 | 30.4 | 0 | 4328.352 | 4328.352 | 11.88%
d) | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 | 80.68 | 10327.04 | 0 | 15.2 | 15.2 | 0 | 1226.336 | 1226.336 | 11.88%
e) | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 | 75.94 | 4860.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
f) | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 | 579.03 | 18528.96 | 0 | 11.4 | 11.4 | 0 | 6600.942 | 6600.942 | 35.62%
g) | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 | 1630.62 | 52179.84 | 0 | 11.4 | 11.4 | 0 | 18589.068 | 18589.068 | 35.62%
h) | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 | 113.91 | 21870.72 | 0 | 45.6 | 45.6 | 0 | 5194.296 | 5194.296 | 23.75%
I) | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 | 85.43 | 16402.56 | 0 | 44.65 | 44.65 | 0 | 3814.4495 | 3814.4495 | 23.26%
j) | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | 128.15 | 4100.8 | 0 | 7.6 | 7.6 | 0 | 973.94 | 973.94 | 23.75%
k) | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | 128.15 | 4100.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
L) | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 | 166.12 | 5315.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Sub Total Fire sealant filling in MCA area for TA |  |  |  | 231547.2 | 0 |  | 0 | 0 | 44717.8205 | 44717.8205 | 19.31%
20 | Fire sealant filling in MCA area for TB
a) | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 | 90.18 | 51943.68 | 0 | 79.8 | 79.8 |  | 7196.364 | 7196.364 | 13.85%
b) | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 | 85.43 | 5467.52 | 0 | 14.25 | 14.25 | 0 | 1217.3775 | 1217.3775 | 22.27%
c) | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 | 142.38 | 36449.28 | 0 | 53.2 | 53.2 | 0 | 7574.616 | 7574.616 | 20.78%
d) | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 | 80.68 | 10327.04 | 0 | 26.6 | 26.6 | 0 | 2146.088 | 2146.088 | 20.78%
e) | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 | 75.94 | 4860.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
f) | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 | 579.03 | 18528.96 | 0 | 13.3 | 13.3 | 0 | 7701.099 | 7701.099 | 41.56%
g) | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 | 1630.62 | 52179.84 | 0 | 13.3 | 13.3 | 0 | 21687.246 | 21687.246 | 41.56%
h) | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 | 113.91 | 21870.72 | 0 | 85.5 | 85.5 | 0 | 9739.305 | 9739.305 | 44.53%
I) | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 | 85.43 | 16402.56 | 0 | 84.55 | 84.55 | 0 | 7223.1065 | 7223.1065 | 44.04%
j) | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | 128.15 | 4100.8 | 0 | 14.25 | 14.25 | 0 | 1826.1375 | 1826.1375 | 44.53%
k) | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | 128.15 | 4100.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
L) | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 | 166.12 | 5315.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Sub Total Fire sealant filling in MCA area for TB |  |  |  | 231547.2 |  |  |  | 0 | 66311.3395 | 66311.3395 | 28.64%
| SUB TOTAL |  |  |  | 463094.4 |  |  |  | 0 | 111029.16 | 111029.16 | 23.98%
| Add CGST @9% |  |  |  | 41678.496 |  |  |  | 0 | 9992.6244 | 9992.6244
| Add SGST @9% |  |  |  | 41678.496 |  |  |  | 0 | 9992.6244 | 9992.6244
| GRAND TOTAL |  |  |  | 546451.392 |  |  |  | 0 | 131014.4088 | 131014.4088

## Actual Certified Qty
ACTUAL CERTIFIED QTY.
BOQ No. | Item Description | Unit | WO Qty | [8 empty] | Cumulative payable | Previous Payable | Current Payable
|  |  |  | Overall Cartridges Supplied at Site | Overall Sealant Supplied at Site (310 ml/tube) in tubes | Overall Sealant installed (310ml/tube) in Tubes | Sealant against installation in [ML] | Required Sealant Thickness per Sleeve | 50% against Supply | 45% against Installation | 5% against T,C & Handingover
[9 empty] | 50% | 45% | 5%
10 | Fire sealant filling in MCA area for TA
10 | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 |  | 61 | 7.8 | 2418 | 0.2 | 39 | 39 |  | 37.05 | 0 | 37.05
20 | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 |  | 10 | 1.52 | 471.2 | 0.19 | 8 | 8 |  | 7.6 | 0 | 7.6
30 | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 |  | 36 | 10.24 | 3174.4 | 0.32 | 32 | 32 |  | 30.4 | 0 | 30.4
40 | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 |  | 11 | 2.88 | 892.8 | 0.18 | 16 | 16 |  | 15.2 | 0 | 15.2
50 | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 |  | 106 | 0 | 0 | 0.17 | 0 | 0 |  | 0 | 0 | 0
60 | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 |  | 104 | 15.36 | 4761.6 | 1.28 | 12 | 12 |  | 11.4 | 0 | 11.4
70 | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 |  | 110 | 27 | 8370 | 2.25 | 12 | 12 |  | 11.4 | 0 | 11.4
80 | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 |  | 31 | 12 | 3720 | 0.25 | 48 | 48 |  | 45.6 | 0 | 45.6
90 | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 |  | 13 | 8.93 | 2768.3 | 0.19 | 47 | 47 |  | 44.65 | 0 | 44.65
100 | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 18 | 2.24 | 694.4 | 0.28 | 8 | 8 |  | 7.6 | 0 | 7.6
110 | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 15 | 0 | 0 | 0.28 | 0 | 0 |  | 0 | 0 | 0
120 | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 |  | 15 | 0 | 0 | 0.37 | 0 | 0 |  | 0 | 0 | 0
[12 empty] | 0 | 0 | 0
| Sub Total Fire sealant filling in MCA area for TA | [10 empty] | 0 | 0 | 0
20 | Fire sealant filling in MCA area for TB | [10 empty] | 0 | 0 | 0
10 | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 |  | 57 | 16.8 | 5208 | 0.2 | 84 | 84 |  | 79.8 | 0 | 79.8
20 | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 |  | 10 | 2.85 | 883.5 | 0.19 | 15 | 15 |  | 14.25 | 0 | 14.25
30 | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 |  | 41 | 17.92 | 5555.2 | 0.32 | 56 | 56 |  | 53.2 | 0 | 53.2
40 | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 |  | 17 | 5.04 | 1562.4 | 0.18 | 28 | 28 |  | 26.6 | 0 | 26.6
50 | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 |  | 100 | 0 | 0 | 0.17 | 0 | 0 |  | 0 | 0 | 0
60 | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 |  | 140 | 17.92 | 5555.2 | 1.28 | 14 | 14 |  | 13.3 | 0 | 13.3
70 | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 |  | 48 | 31.5 | 9765 | 2.25 | 14 | 14 |  | 13.3 | 0 | 13.3
80 | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 |  | 42 | 22.5 | 6975 | 0.25 | 90 | 90 |  | 85.5 | 0 | 85.5
90 | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 |  | 13 | 16.91 | 5242.1 | 0.19 | 89 | 89 |  | 84.55 | 0 | 84.55
100 | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 18 | 4.2 | 1302 | 0.28 | 15 | 15 |  | 14.25 | 0 | 14.25
110 | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 19 | 0 | 0 | 0.28 | 0 | 0 |  | 0 | 0 | 0
120 | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 |  | 15 | 0 | 0 | 0.37 | 0 | 0 |  | 0 | 0 | 0
| Sub Total Fire sealant filling in MCA area for TB | [11 empty] | 0 | 0

## Supply Summary
SUPPLY SUMMARY
Item no | BOQ Sr. No | Item Text | Item Description | Unit | Order Qty |  | RA 01 |  |  |  | RA 02 |  |  |  | RA03
[6 empty] | MIR No. | 2038-0035 | 2088-0035 | 2721-0035 | Sub-total RA01 | 1 | 34 & 35 | 36 | Sub-total RA02 | 38 | 76 | Sub-total RA03 | Cumulative supplied till date
[6 empty] | DC Date | 06.01.2022 | 12.01.2022 | 30.03.2022 |  | 19.12.20 | 25.03.21 | 09.04.21 |  | 10.06.21 | 20.01.22
[6 empty] | D.C. No. | 781/21-22 | 800/21-22 | 1119/21-22 |  | 572 | 706 | 708 |  | 15 | 237
10 | 10 | Fire sealant filling in MCA area for TA | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 |  | 17 | 27 | 17 | 61 |  |  |  | 0 |  |  | 0 | 61
10 | 20 | Fire sealant filling in MCA area for TA | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 |  | 2 | 4 | 4 | 10 |  |  |  | 0 |  |  | 0 | 10
10 | 30 | Fire sealant filling in MCA area for TA | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 |  | 11 | 15 | 10 | 36 |  |  |  | 0 |  |  | 0 | 36
10 | 40 | Fire sealant filling in MCA area for TA | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 |  | 3 | 4 | 4 | 11 |  |  |  | 0 |  |  | 0 | 11
10 | 50 | Fire sealant filling in MCA area for TA | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 |  | 32 | 42 | 32 | 106 |  |  |  | 0 |  |  | 0 | 106
10 | 60 | Fire sealant filling in MCA area for TA | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 |  | 28 | 38 | 38 | 104 |  |  |  | 0 |  |  | 0 | 104
10 | 70 | Fire sealant filling in MCA area for TA | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 |  | 40 | 35 | 35 | 110 |  |  |  | 0 |  |  | 0 | 110
10 | 80 | Fire sealant filling in MCA area for TA | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 |  | 9 | 11 | 11 | 31 |  |  |  | 0 |  |  | 0 | 31
10 | 90 | Fire sealant filling in MCA area for TA | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 |  | 3 | 5 | 5 | 13 |  |  |  | 0 |  |  | 0 | 13
10 | 100 | Fire sealant filling in MCA area for TA | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 4 | 8 | 6 | 18 |  |  |  | 0 |  |  | 0 | 18
10 | 110 | Fire sealant filling in MCA area for TA | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 5 | 6 | 4 | 15 |  |  |  | 0 |  |  | 0 | 15
10 | 120 | Fire sealant filling in MCA area for TA | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 |  | 5 | 5 | 5 | 15 | [7 empty] | 15
20 | 10 | Fire sealant filling in MCA area for TB | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 |  | 17 | 20 | 20 | 57 |  |  |  | 0 |  |  | 0 | 57
20 | 20 | Fire sealant filling in MCA area for TB | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 |  | 2 | 4 | 4 | 10 |  |  |  | 0 |  |  | 0 | 10
20 | 30 | Fire sealant filling in MCA area for TB | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 |  | 11 | 15 | 15 | 41 |  |  |  | 0 |  |  | 0 | 41
20 | 40 | Fire sealant filling in MCA area for TB | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 |  | 3 | 8 | 6 | 17 |  |  |  | 0 |  |  | 0 | 17
20 | 50 | Fire sealant filling in MCA area for TB | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 |  | 30 | 40 | 30 | 100 |  |  |  | 0 |  |  | 0 | 100
20 | 60 | Fire sealant filling in MCA area for TB | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 |  | 40 | 50 | 50 | 140 |  |  |  | 0 |  |  | 0 | 140
20 | 70 | Fire sealant filling in MCA area for TB | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 |  | 12 | 18 | 18 | 48 |  |  |  | 0 |  |  | 0 | 48
20 | 80 | Fire sealant filling in MCA area for TB | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 |  | 9 | 19 | 14 | 42 |  |  |  | 0 |  |  | 0 | 42
20 | 90 | Fire sealant filling in MCA area for TB | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 |  | 3 | 5 | 5 | 13 |  |  |  | 0 |  |  | 0 | 13
20 | 100 | Fire sealant filling in MCA area for TB | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 4 | 8 | 6 | 18 |  |  |  | 0 |  |  | 0 | 18
20 | 110 | Fire sealant filling in MCA area for TB | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 |  | 5 | 8 | 6 | 19 |  |  |  | 0 |  |  | 0 | 19
20 | 120 | Fire sealant filling in MCA area for TB | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 |  | 5 | 5 | 5 | 15 | [7 empty] | 15

## Installation Summary
INSTALLATION SUMMARY
Item no | BOQ Sr. No | Item Text | Item Description | Unit | Order Qty | WIR - 7307 | WIR - 7691 | WIR - 7385 | WIR - 7386 | WIR - 7387 | WIR - 7388 | WIR - 7389 | WIR - 7690 | [7 empty] | RA 01 |  | RA 02 |  | RA 03 |  | Cumulative Installation till date
[6 empty] | Location - 36 | Location - 37 | Location - 38 | Location - 39 | Location - 40 | Location - 41 | Location - 42 | Location - 43 | [7 empty] | WIR 1 | Sub-total RA01 | WIR 2 | Sub-total RA02 | WIR 3 | Sub-total RA03
10 | 10 | Fire sealant filling in MCA area for TA | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 | 3 | 7 | 9 | 4 | 4 | 2 | 6 | 4 | [7 empty] | 39 | 39 |  | 0 |  | 0 | 39
10 | 20 | Fire sealant filling in MCA area for TA | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 8 | 8 |  | 0 |  | 0 | 8
10 | 30 | Fire sealant filling in MCA area for TA | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [7 empty] | 32 | 32 |  | 0 |  | 0 | 32
10 | 40 | Fire sealant filling in MCA area for TA | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [7 empty] | 16 | 16 |  | 0 |  | 0 | 16
10 | 50 | Fire sealant filling in MCA area for TA | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 | [15 empty] | 0 | 0 |  | 0 |  | 0 | 0
10 | 60 | Fire sealant filling in MCA area for TA | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [7 empty] | 12 | 12 |  | 0 |  | 0 | 12
10 | 70 | Fire sealant filling in MCA area for TA | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [7 empty] | 12 | 12 |  | 0 |  | 0 | 12
10 | 80 | Fire sealant filling in MCA area for TA | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [7 empty] | 48 | 48 |  | 0 |  | 0 | 48
10 | 90 | Fire sealant filling in MCA area for TA | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | [7 empty] | 47 | 47 |  | 0 |  | 0 | 47
10 | 100 | Fire sealant filling in MCA area for TA | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 8 | 8 |  | 0 |  | 0 | 8
10 | 110 | Fire sealant filling in MCA area for TA | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | [15 empty] | 0 | 0 |  | 0 |  | 0 | 0
10 | 120 | Fire sealant filling in MCA area for TA | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 | [15 empty] | 0 | 0 |  | 0 |  | 0 | 0
[6 empty] | WIR - 8228 | WIR - 8230 | WIR - 8231 | WIR - 8232 | WIR - 8234 | WIR - 8235 | WIR - 8236 | WIR - 8237 | WIR - 8238 | WIR - 8239 | WIR - 8240 | WIR - 8241 | WIR - 8242 | WIR - 8243 | WIR - 8246
[6 empty] | Location - 31 | Location - 32 | Location - 33 | Location - 34 | Location - 35 | Location - 36 | Location - 37 | Location - 38 | Location - 39 | Location - 40 | Location - 41 | Location - 42 | Location - 43 | Location - 44 | Location - 45 |  | 0 |  | 0 |  | 0 | 0
[22 empty] | 0 |  | 0 |  | 0 | 0
20 | 10 | Fire sealant filling in MCA area for TB | 50mm dia core X 32mm dia pipe X200mm depth | NOS | 576 | 4 | 7 | 9 | 9 | 7 | 7 | 7 | 6 | 5 | 5 | 4 | 6 | 4 | 4 |  | 84 | 84 |  | 0 |  | 0 | 84
20 | 20 | Fire sealant filling in MCA area for TB | 50mm dia core X 12mm dia pipe X100mm depth | NOS | 64 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 15 | 15 |  | 0 |  | 0 | 15
20 | 30 | Fire sealant filling in MCA area for TB | 80mm dia core X 50mm dia pipe X200mm depth | NOS | 256 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 56 | 56 |  | 0 |  | 0 | 56
20 | 40 | Fire sealant filling in MCA area for TB | 80mm dia core X 65mm dia pipe X200mm depth | NOS | 128 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 28 | 28 |  | 0 |  | 0 | 28
20 | 50 | Fire sealant filling in MCA area for TB | 50mm dia core X 20mm dia pipe X200mm depth | NOS | 64 | [15 empty] | 0 | 0 |  | 0 |  | 0 | 0
20 | 60 | Fire sealant filling in MCA area for TB | 150mm dia core X 80mm dia pipe X200mm depth | NOS | 32 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 14 | 14 |  | 0 |  | 0 | 14
20 | 70 | Fire sealant filling in MCA area for TB | 150mm dia core X 75mm dia pipe X200mm depth | NOS | 32 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 14 | 14 |  | 0 |  | 0 | 14
20 | 80 | Fire sealant filling in MCA area for TB | 75mm dia core X 50mm dia pipe X425mm depth | NOS | 192 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 90 | 90 |  | 0 |  | 0 | 90
20 | 90 | Fire sealant filling in MCA area for TB | 50mm dia core X 12mm dia pipe X425mm depth | NOS | 192 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 89 | 89 |  | 0 |  | 0 | 89
20 | 100 | Fire sealant filling in MCA area for TB | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 15 | 15 |  | 0 |  | 0 | 15
20 | 110 | Fire sealant filling in MCA area for TB | 100mm dia core X 80mm dia pipe X230mm depth | NOS | 32 | [15 empty] | 0 | 0 |  | 0 |  | 0 | 0
20 | 110 | Fire sealant filling in MCA area for TB | 75mm dia core X 32mm dia pipe X230mm depth | NOS | 32 | [15 empty] | 0 | 0 |  | 0 |  | 0 | 0

## DAY CARE (hidden)
TEAMONE HVAC SERVICES PVT. LTD.
DUCTING MEASUREMENT
PROJECT NAME : OBEROI ETERNIA - MULUND ( CLUBHOUSE )
Sr. No. | Description | Width | Height | Width | Height | Perimeter | Length | Qty | Area (Sq.Mtr.) | Ducting |  | Thermal Insulation | Accoustic Insulation | Flexible Duct | Canvas Connection | Remarks
[10 empty] | 24 G | 22 G
DAY CARE
IDU-01
1 | CANVAS | 1190 | 385 | 1190 | 385 | 3150 |  | 1 | [6 empty] | 3.15
2 | CON | 1190 | 385 | 1000 | 250 | 2825 | 600 | 1 | 1.695 |  | 1.695 |  | 1.695
3 | ST | 1000 | 250 | 1000 | 250 | 2500 | 510 | 1 | 1.275 |  | 1.275 |  | 1.275 |  |  | 982
4 | EL | 1000 | 250 | 1000 | 250 | 2500 | 1600 | 1 | 4 |  | 4 |  | 4
5 | ST | 1000 | 250 | 1000 | 250 | 2500 | 510 | 1 | 1.275 |  | 1.275 | 1.5567 |  |  |  | 805
6 | ST | 1000 | 250 | 1000 | 250 | 2500 | 1120 | 3 | 8.4 |  | 8.4 | 9.3403
7 | Y-EL-01 | 450 | 250 | 450 | 250 | 1400 | 500 | 1 | 0.7 |  | 0.7 | 0.8712
8 | Y-TP-02 | 546 | 250 | 700 | 250 | 1746 | 660 | 1 | 1.1524 |  | 1.1524 | 1.3665
9 | TP | 450 | 250 | 600 | 250 | 1550 | 580 | 1 | 0.899 | 0.899 |  | 1.0894
10 | ST | 600 | 250 | 600 | 250 | 1700 | 510 | 1 | 0.867 | 0.867 |  | 1.0687
11 | ST | 600 | 250 | 600 | 250 | 1700 | 1120 | 1 | 1.904 | 1.904 |  | 2.1374
12 | ST | 600 | 250 | 600 | 250 | 1700 | 510 | 1 | 0.867 | 0.867 |  | 1.0687
13 | ST | 600 | 250 | 600 | 250 | 1700 | 1120 | 1 | 1.904 | 1.904 |  | 2.1374
14 | TP | 600 | 250 | 350 | 250 | 1450 | 975 | 1 | 1.4138 | 1.4138 |  | 1.6146
15 | ST | 350 | 250 | 350 | 250 | 1200 | 510 | 1 | 0.612 | 0.612 |  | 0.76372
16 | ST | 350 | 250 | 350 | 250 | 1200 | 1120 | 1 | 1.344 | 1.344 |  | 1.5274
17 | ST | 350 | 250 | 350 | 250 | 1200 | 1200 | 1 | 1.44 | 1.44 |  | 1.6276
18 | D/E | 400 | 300 |  |  |  | 0 | 1 | 0.12 | 0.12 |  | 0.12
19 | ST | 700 | 250 | 700 | 250 | 1900 | 510 | 1 | 0.969 | 0.969 |  | 1.1907
20 | EL | 700 | 250 | 700 | 250 | 1900 | 1000 | 1 | 1.9 | 1.9 |  | 2.1472
21 | ST | 700 | 250 | 700 | 250 | 1900 | 1120 | 1 | 2.128 | 2.128 |  | 2.3814
22 | ST | 700 | 250 | 700 | 250 | 1900 | 510 | 1 | 0.969 | 0.969 |  | 1.1907
23 | ST | 700 | 250 | 700 | 250 | 1900 | 1120 | 1 | 2.128 | 2.128 |  | 2.3814
24 | TP | 700 | 250 | 350 | 250 | 1550 | 615 | 1 | 0.95325 | 0.95325 |  | 1.1454
25 | ST | 350 | 250 | 350 | 250 | 1200 | 510 | 2 | 1.224 | 1.224 |  | 1.5274
26 | ST | 350 | 250 | 350 | 250 | 1200 | 1120 | 2 | 2.688 | 2.688 |  | 3.0549
27 | TP | 350 | 250 | 150 | 250 | 1000 | 500 | 1 | 0.5 | 0.5 |  | 0.6312
28 | ST | 150 | 250 | 150 | 250 | 800 | 1010 | 1 | 0.808 | 0.808 |  | 0.94572
29 | D/E | 200 | 300 |  |  |  | 0 | 1 | 0.06 | 0.06 |  | 0.06
30 | SHU-COL | 275 | 200 | 200 | 200 | 875 | 250 | 8 | 1.75 | 1.75 |  | 2.5956
31 | D/E | 250 | 250 |  |  | 500 | 0 | 8 | 0.5 | 0.5 |  | 0.4416
32 | SHU-COL | 275 | 200 | 200 | 200 | 875 | 280 | 10 | 2.45 | 2.45 |  | 3.5226
33 | D/E | 250 | 250 |  |  | 500 | 0 | 10 | 0.625 | 0.625 |  | 0.552
34 | RING | 150 |  |  |  | 471 | 150 | 18 | 1.2717 | 1.2717 |  | 1.2717
35 | FLEXIBLE DUCT | 150 |  |  |  |  | 475 | 18 | [5 empty] | 8.55
RETURN AIR
36 | RAD-01 | 700 | 350 | 700 | 350 | 2100 | 700 | 1 | 1.47 | 1.47 |  |  | 1.47
TOTAL | [8 empty] | 52.2621 | 33.7647 | 18.4974 | 51.3295 | 8.44 | 8.55 | 3.15
[9 empty] | SQMTR | SQMTR |  | SQMTR | SQMTR | SQMTR | RMT

## CAFE (hidden)
TEAMONE HVAC SERVICES PVT. LTD.
DUCTING MEASUREMENT
PROJECT NAME : OBEROI ETERNIA - MULUND ( CLUBHOUSE )
Sr. No. | Description | Width | Height | Width | Height | Perimeter | Length | Qty | Area (Sq.Mtr.) | Ducting |  |  | Thermal Insulation | Accoustic Insulation | Flexible Duct | Canvas Connection | Remarks
[10 empty] | 24 G | 22 G | 20 G
CAFÉ
1 | CANVAS | 1190 | 385 | 1190 | 385 | 3150 |  | 2 | [7 empty] | 6.3
2 | CON | 1190 | 385 | 680 | 330 | 2585 | 670 | 2 | 3.4639 |  | 3.4639 |  |  | 3.4639
3 | G.L. COLLAR | 715 | 365 | 715 | 300 | 2095 | 200 | 2 | 0.838 |  | 0.838 |  |  | 0.838
4 | PLNM-ST | 1300 | 400 | 1300 | 400 | 3400 | 1170 | 1 | 3.978 |  |  | 3.978 |  | 3.978
5 | PLNM-ST | 1300 | 400 | 1300 | 400 | 3400 | 510 | 1 | 1.734 |  |  | 1.734 |  | 1.734
6 | PLNM-ST | 1300 | 400 | 1300 | 400 | 3400 | 1520 | 1 | 5.168 |  |  | 5.168 |  | 5.168
7 | D/E | 1300 | 400 |  |  | 1700 |  | 2 | 1.04 |  |  | 1.04 |  | 1.04
8 | COLLAR | 700 | 300 | 700 | 300 | 2000 | 100 | 1 | 0.2 |  | 0.2 |  |  | 0.2
9 | OFF-TP | 700 | 300 | 700 | 275 | 1975 | 420 | 1 | 0.8295 |  | 0.8295 |  |  | 0.8295
10 | ST | 700 | 275 | 700 | 275 | 1950 | 720 | 1 | 1.404 |  | 1.404 |  | 1.6416
11 | OFF-TP | 700 | 275 | 700 | 300 | 1975 | 370 | 1 | 0.73075 |  | 0.73075 |  | 0.95269
12 | 45-EL | 700 | 300 | 700 | 300 | 2000 | 350 | 1 | 0.7 |  | 0.7 |  | 0.9234
13 | ST | 700 | 300 | 700 | 300 | 2000 | 1120 | 1 | 2.24 |  | 2.24 |  | 2.5034
14 | 45-EL | 700 | 300 | 700 | 300 | 2000 | 350 | 1 | 0.7 |  | 0.7 |  | 0.9234
15 | ST | 700 | 300 | 700 | 300 | 2000 | 750 | 1 | 1.5 | 1.5 |  |  | 1.7442
16 | TP | 700 | 300 | 550 | 300 | 1850 | 750 | 1 | 1.3875 | 1.3875 |  |  | 1.6167
17 | ST | 550 | 300 | 550 | 300 | 1700 | 1120 | 4 | 7.616 | 7.616 |  |  | 8.5498
18 | TP | 550 | 300 | 400 | 300 | 1550 | 450 | 1 | 0.6975 | 0.6975 |  |  | 0.8811
19 | ST | 400 | 300 | 400 | 300 | 1400 | 890 | 1 | 1.246 | 1.246 |  |  | 1.4375
20 | ST | 400 | 300 | 400 | 300 | 1400 | 1120 | 2 | 3.136 | 3.136 |  |  | 3.5429
21 | TP | 400 | 300 | 300 | 250 | 1250 | 380 | 1 | 0.475 | 0.475 |  |  | 0.62496
22 | ST | 300 | 250 | 300 | 250 | 1100 | 510 | 1 | 0.561 | 0.561 |  |  | 0.70272
23 | ST | 300 | 250 | 300 | 250 | 1100 | 1120 | 1 | 1.232 | 1.232 |  |  | 1.4054
24 | ST | 300 | 250 | 300 | 250 | 1100 | 1170 | 1 | 1.287 | 1.287 |  |  | 1.463
25 | D/E | 350 | 300 |  |  |  |  | 1 | 0.105 | 0.105 |  |  | 0.105
26 | COLLAR | 700 | 300 | 700 | 300 | 2000 | 100 | 1 | 0.2 |  | 0.2 |  |  | 0.2
27 | OFF-TP | 700 | 300 | 700 | 275 | 1975 | 420 | 1 | 0.8295 |  | 0.8295 |  |  | 0.8295
28 | ST | 700 | 275 | 700 | 275 | 1950 | 550 | 1 | 1.0725 |  | 1.0725 |  | 1.3013
29 | OFF-TP | 700 | 227 | 700 | 300 | 1927 | 400 | 1 | 0.7708 |  | 0.7708 |  | 0.9895
30 | ST | 700 | 300 | 700 | 300 | 2000 | 1120 | 1 | 2.24 | 2.24 |  |  | 2.5034
| ST | 700 | 300 | 700 | 300 | 2000 | 350 | 1 | 0.7 | 0.7 |  |  | 0.9234
31 | ST | 700 | 300 | 700 | 300 | 2000 | 1120 | 2 | 4.48 | 4.48 |  |  | 5.0069
32 | ST | 700 | 300 | 700 | 300 | 2000 | 915 | 1 | 1.83 | 1.83 |  |  | 2.0828
33 | TP | 700 | 300 | 550 | 300 | 1850 | 450 | 1 | 0.8325 | 0.8325 |  |  | 1.0461
34 | ST | 550 | 300 | 550 | 300 | 1700 | 1120 | 3 | 5.712 | 5.712 |  |  | 6.4123
35 | TP | 550 | 300 | 400 | 300 | 1550 | 300 | 1 | 0.465 | 0.465 |  |  | 0.6408
36 | ST | 400 | 300 | 400 | 300 | 1400 | 510 | 1 | 0.714 | 0.714 |  |  | 0.88572
37 | ST | 400 | 300 | 400 | 300 | 1400 | 1120 | 1 | 1.568 | 1.568 |  |  | 1.7714
| ST | 400 | 300 | 400 | 300 | 1400 | 580 | 1 | 0.812 | 0.812 |  |  | 0.98736
38 | ST | 400 | 300 | 400 | 300 | 1400 | 1120 | 1 | 1.568 | 1.568 |  |  | 1.7714
39 | TP | 400 | 300 | 250 | 300 | 1250 | 515 | 1 | 0.64375 | 0.64375 |  |  | 0.80073
40 | ST | 250 | 300 | 250 | 300 | 1100 | 1120 | 1 | 1.232 | 1.232 |  |  | 1.4054
41 | ST | 250 | 300 | 250 | 300 | 1100 | 1170 | 1 | 1.287 | 1.287 |  |  | 1.463
42 | D/E | 300 | 350 |  |  |  | 0 | 1 | 0.105 | 0.105 |  |  | 0.105
43 | SHU-BR | 300 | 250 | 250 | 250 | 1050 | 135 | 1 | 0.14175 | 0.14175 |  |  | 0.25897
44 | ST | 250 | 250 | 250 | 250 | 1000 | 505 | 1 | 0.505 | 0.505 |  |  | 0.63646
45 | Y-EL-01 | 125 | 250 | 125 | 250 | 750 | 250 | 1 | 0.1875 | 0.1875 |  |  | 0.2807
46 | Y-EL-02 | 125 | 250 | 125 | 250 | 750 | 250 | 1 | 0.1875 | 0.1875 |  |  | 0.2807
47 | TP | 125 | 250 | 150 | 250 | 775 | 200 | 1 | 0.155 | 0.155 |  |  | 0.2481
48 | ST | 150 | 250 | 150 | 250 | 800 | 660 | 1 | 0.528 | 0.528 |  |  | 0.64752
49 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.0552
50 | TP | 125 | 250 | 150 | 250 | 775 | 200 | 1 | 0.155 | 0.155 |  |  | 0.2481
51 | ST | 150 | 250 | 150 | 250 | 800 | 660 | 1 | 0.528 | 0.528 |  |  | 0.64752
52 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
53 | SHU-BR | 300 | 250 | 300 | 250 | 1100 | 135 | 1 | 0.1485 | 0.1485 |  |  | 0.27072
54 | ST | 300 | 250 | 300 | 250 | 1100 | 505 | 1 | 0.5555 | 0.5555 |  |  | 0.69696
55 | Y-EL-01 | 125 | 250 | 125 | 250 | 750 | 250 | 1 | 0.1875 | 0.1875 |  |  | 0.2807
56 | Y-EL-02 | 125 | 250 | 125 | 250 | 750 | 250 | 1 | 0.1875 | 0.1875 |  |  | 0.2807
57 | TP | 125 | 250 | 150 | 250 | 775 | 200 | 1 | 0.155 | 0.155 |  |  | 0.2481
58 | ST | 150 | 250 | 150 | 250 | 800 | 660 | 1 | 0.528 | 0.528 |  |  | 0.64752
59 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
60 | TP | 125 | 250 | 150 | 250 | 775 | 300 | 1 | 0.2325 | 0.2325 |  |  | 0.3308
61 | ST | 150 | 250 | 150 | 250 | 800 | 765 | 1 | 0.612 | 0.612 |  |  | 0.73698
62 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
63 | SHU-BR | 300 | 250 | 300 | 250 | 1100 | 135 | 1 | 0.1485 | 0.1485 |  |  | 0.27072
64 | ST | 250 | 250 | 250 | 250 | 1000 | 505 | 1 | 0.505 | 0.505 |  |  | 0.63646
65 | Y-EL-01 | 125 | 250 | 125 | 250 | 750 | 250 | 1 | 0.1875 | 0.1875 |  |  | 0.2807
66 | Y-EL-02 | 125 | 250 | 125 | 250 | 750 | 250 | 1 | 0.1875 | 0.1875 |  |  | 0.2807
67 | TP | 125 | 250 | 150 | 250 | 775 | 200 | 1 | 0.155 | 0.155 |  |  | 0.2481
68 | ST | 150 | 250 | 150 | 250 | 800 | 660 | 1 | 0.528 | 0.528 |  |  | 0.64752
69 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
70 | TP | 125 | 250 | 150 | 250 | 775 | 300 | 1 | 0.2325 | 0.2325 |  |  | 0.3308
71 | ST | 150 | 250 | 150 | 250 | 800 | 765 | 1 | 0.612 | 0.612 |  |  | 0.73698
72 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
73 | SHU-BR | 550 | 250 | 500 | 250 | 1550 | 135 | 1 | 0.20925 | 0.20925 |  |  | 0.37647
74 | ST | 500 | 250 | 500 | 250 | 1500 | 450 | 1 | 0.675 | 0.675 |  |  | 0.8536
75 | Y-EL-01 | 350 | 250 | 350 | 250 | 1200 | 435 | 1 | 0.522 | 0.522 |  |  | 0.66982
76 | Y-EL-02 | 150 | 250 | 150 | 250 | 800 | 280 | 1 | 0.224 | 0.224 |  |  | 0.32376
77 | ST | 350 | 250 | 350 | 250 | 1200 | 955 | 1 | 1.146 | 1.146 |  |  | 1.3209
78 | TP | 350 | 250 | 150 | 250 | 1000 | 555 | 1 | 0.555 | 0.555 |  |  | 0.68906
79 | ST | 150 | 250 | 150 | 250 | 800 | 1200 | 1 | 0.96 | 0.96 |  |  | 1.1076
80 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
81 | ST | 150 | 250 | 150 | 250 | 800 | 1010 | 1 | 0.808 | 0.808 |  |  | 0.94572
82 | D/E | 200 | 300 |  |  | 500 |  | 1 | 0.06 | 0.06 |  |  | 0.06
83 | SHO COL | 275 | 200 | 200 | 200 | 875 | 150 | 16 | 2.1 | 2.1 |  |  | 3.708
84 | SHO COL | 275 | 200 | 200 | 200 | 875 | 100 | 2 | 0.175 | 0.175 |  |  | 0.3708
85 | ST | 200 | 200 | 200 | 200 | 800 | 200 | 16 | 2.56 | 2.56 |  |  | 4.0896
86 | ST | 200 | 200 | 200 | 200 | 800 | 100 | 2 | 0.16 | 0.16 |  |  | 0.3408
87 | SHU COLL | 275 | 200 | 200 | 200 | 875 | 150 | 18 | 2.3625 | 2.3625 |  |  | 4.1715
88 | ST | 200 | 200 | 200 | 200 | 800 | 800 | 18 | 11.52 | 11.52 |  |  | 13.8024
89 | D/E | 250 | 250 |  |  | 500 |  | 36 | 2.25 | 2.25 |  |  | 2.25
90 | RING | 150 |  |  |  | 471 | 150 | 36 | 2.5434 | 2.5434 |  |  | 2.5434
91 | FLEXIBLE DUCT | 150 |  |  |  |  | 600 | 18 | [6 empty] | 10.8
92 | FLEXIBLE DUCT | 150 |  |  |  |  | 650 | 18 | [6 empty] | 11.7
TOTAL | [8 empty] | 106.1316 | 80.2327 | 13.9789 | 11.92 | 107.3257 | 18.2809 | 22.5 | 6.3
[9 empty] | SQMTR | SQMTR | SQMTR | SQMTR | SQMTR | SQMTR | RMT | RMT

## GYM (hidden)
TEAMONE HVAC SERVICES PVT. LTD.
DUCTING MEASUREMENT
PROJECT NAME : OBEROI ETERNIA - MULUND ( CLUBHOUSE )
Sr. No. | Description | Width | Height | Width | Height | Perimeter | Length | Qty | Area (Sq.Mtr.) | Ducting |  | Thermal Insulation | Accoustic Insulation | Flexible Duct | Canvas Connection | Remarks
[10 empty] | 24 G | 22 G
GYM Area
IDU-4A
1 | ST | 800 | 300 | 800 | 300 | 2200 | 600 | 1 | 1.32 |  | 1.32 | 1.5764
2 | OFF | 800 | 300 | 800 | 300 | 2200 | 450 | 1 | 0.99 |  | 0.99 | 1.2386
3 | ST | 800 | 300 | 800 | 300 | 2200 | 1120 | 1 | 2.464 |  | 2.464 | 2.7474
4 | TP | 800 | 300 | 800 | 250 | 2150 | 342 | 1 | 0.7353 |  | 0.7353 | 0.97328
5 | ST | 800 | 250 | 800 | 250 | 2100 | 1120 | 1 | 2.352 |  | 2.352 | 2.6254
6 | EL | 800 | 250 | 800 | 250 | 2100 | 1000 | 1 | 2.1 |  | 2.1 | 2.3672
7 | ST | 800 | 250 | 800 | 250 | 2100 | 1120 | 5 | 11.76 |  | 11.76 | 13.1272
8 | Y-EL-01 | 400 | 250 | 400 | 250 | 1300 | 471 | 1 | 0.6123 | 0.6123 |  | 0.77199
9 | Y-EL-02 | 400 | 250 | 400 | 250 | 1300 | 471 | 1 | 0.6123 | 0.6123 |  | 0.77199
10 | TP | 400 | 250 | 450 | 250 | 1350 | 550 | 1 | 0.7425 | 0.7425 |  | 0.9113
11 | ST | 450 | 250 | 450 | 250 | 1400 | 1120 | 2 | 3.136 | 3.136 |  | 3.5429
12 | ST | 450 | 250 | 450 | 250 | 1400 | 510 | 1 | 0.714 | 0.714 |  | 0.88572
13 | Y-EL-01 | 250 | 225 | 250 | 225 | 950 | 334 | 1 | 0.3173 | 0.3173 |  | 0.43487
14 | Y-EL-02 | 250 | 225 | 250 | 225 | 950 | 334 | 1 | 0.3173 | 0.3173 |  | 0.43487
15 | TP | 250 | 225 | 250 | 300 | 1025 | 300 | 1 | 0.3075 | 0.3075 |  | 0.4308
16 | ST | 250 | 300 | 250 | 300 | 1100 | 945 | 1 | 1.0395 | 1.0395 |  | 1.2038
17 | D/E | 250 | 300 |  |  | 550 | 0 | 1 | 0.075 | 0.075 |  | 0.075
18 | TP | 250 | 225 | 250 | 300 | 1025 | 300 | 1 | 0.3075 | 0.3075 |  | 0.4308
19 | ST | 250 | 300 | 250 | 300 | 1100 | 945 | 1 | 1.0395 | 1.0395 |  | 1.2038
20 | D/E | 250 | 300 |  |  | 550 | 0 | 1 | 0.075 | 0.075 |  | 0.075
21 | TP | 400 | 250 | 450 | 250 | 1350 | 564 | 1 | 0.7614 | 0.7614 |  | 0.93093
22 | ST | 450 | 250 | 450 | 250 | 1400 | 1000 | 1 | 1.4 | 1.4 |  | 1.5972
23 | Y-EL-01 | 250 | 225 | 250 | 225 | 950 | 334 | 1 | 0.3173 | 0.3173 |  | 0.43487
24 | Y-EL-02 | 250 | 225 | 250 | 225 | 950 | 334 | 1 | 0.3173 | 0.3173 |  | 0.43487
25 | TP | 225 | 250 | 300 | 250 | 1025 | 350 | 1 | 0.35875 | 0.35875 |  | 0.48465
26 | ST | 300 | 250 | 300 | 250 | 1100 | 1004 | 1 | 1.1044 | 1.1044 |  | 1.2718
27 | D/E | 300 | 250 |  |  | 550 | 0 | 1 | 0.075 | 0.075 |  | 0.075
28 | TP | 225 | 250 | 300 | 250 | 1025 | 350 | 1 | 0.35875 | 0.35875 |  | 0.48465
29 | ST | 300 | 250 | 300 | 250 | 1100 | 985 | 1 | 1.0835 | 1.0835 |  | 1.2499
30 | D/E | 300 | 250 |  |  | 550 | 0 | 1 | 0.075 | 0.075 |  | 0.075
31 | SHU-BR | 350 | 250 | 300 | 250 | 1150 | 150 | 1 | 0.1725 | 0.1725 |  | 0.3005
32 | ST | 300 | 250 | 300 | 250 | 1100 | 1553 | 1 | 1.7083 | 1.7083 |  | 1.9043
33 | D/E | 300 | 250 |  |  | 550 | 0 | 1 | 0.075 | 0.075 |  | 0.0602
34 | SHU-COL | 325 | 200 | 250 | 200 | 975 | 150 | 8 | 1.17 | 1.17 |  | 2.054
35 | ST | 250 | 200 | 250 | 200 | 900 | 200 | 6 | 1.08 | 1.08 |  | 1.7136
36 | D/E | 250 | 200 |  |  | 450 | 0 | 10 | 0.5 | 0.5 |  | 0.502
37 | ST | 250 | 200 | 250 | 200 | 900 | 270 | 2 | 0.486 | 0.486 |  | 0.70448
38 | RING | 200 |  |  |  | 628 | 150 | 10 | 0.942 | 0.942 |  | 0.942
39 | FLEXIBLE DUCT | 200 |  |  |  |  | 800 | 10 | [5 empty] | 8
IDU-4B
1 | ST | 800 | 300 | 800 | 300 | 2200 | 600 | 1 | 1.32 |  | 1.32 | 1.5764
2 | OFF | 800 | 300 | 800 | 300 | 2200 | 550 | 1 | 1.21 |  | 1.21 | 1.4638
3 | ST | 800 | 300 | 800 | 300 | 2200 | 1120 | 5 | 12.32 |  | 12.32 | 13.7372
4 | Y-EL-01 | 450 | 300 | 500 | 300 | 1550 | 510 | 1 | 0.7905 | 0.7905 |  | 0.97722
5 | Y-EL-02 | 350 | 300 | 350 | 300 | 1300 | 510 | 1 | 0.663 | 0.663 |  | 0.82472
6 | EL | 500 | 300 | 500 | 300 | 1600 | 1000 | 1 | 1.6 | 1.6 |  | 1.8172
7 | Y-EL-01 | 250 | 300 | 250 | 300 | 1100 | 395 | 1 | 0.4345 | 0.4345 |  | 0.57024
8 | Y-EL-02 | 250 | 300 | 250 | 300 | 1100 | 395 | 1 | 0.4345 | 0.4345 |  | 0.57024
9 | ST | 250 | 300 | 250 | 300 | 1100 | 1170 | 1 | 1.287 | 1.287 |  | 1.463
10 | D/E | 300 | 350 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
0
11 | ST | 350 | 300 | 350 | 300 | 1300 | 1120 | 1 | 1.456 | 1.456 |  | 1.6494
12 | TP | 350 | 300 | 250 | 300 | 1200 | 350 | 1 | 0.42 | 0.42 |  | 0.5634
13 | ST | 250 | 300 | 250 | 300 | 1100 | 940 | 1 | 1.034 | 1.034 |  | 1.1981
14 | D/E | 300 | 350 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
0
15 | ST | 350 | 300 | 350 | 300 | 1300 | 1120 | 3 | 4.368 | 4.368 |  | 4.9483
16 | EL | 350 | 300 | 350 | 300 | 1300 | 1050 | 1 | 1.365 | 1.365 |  | 1.5548
17 | ST | 350 | 300 | 350 | 300 | 1300 | 510 | 1 | 0.663 | 0.663 |  | 0.82472
18 | Y-EL-01 | 175 | 300 | 175 | 300 | 950 | 300 | 1 | 0.285 | 0.285 |  | 0.4008
19 | Y-EL-02 | 175 | 300 | 175 | 300 | 950 | 300 | 1 | 0.285 | 0.285 |  | 0.4008
20 | TP | 175 | 300 | 250 | 300 | 1025 | 300 | 1 | 0.3075 | 0.3075 |  | 0.4308
21 | ST | 250 | 300 | 250 | 300 | 1100 | 990 | 1 | 1.089 | 1.089 |  | 1.2557
22 | D/E | 300 | 350 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
0
23 | TP | 175 | 300 | 250 | 300 | 1025 | 300 | 1 | 0.3075 | 0.3075 |  | 0.4308
24 | ST | 250 | 300 | 250 | 300 | 1100 | 1105 | 1 | 1.2155 | 1.2155 |  | 1.3882
25 | D/E | 300 | 350 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
26 | SHU-COL | 325 | 200 | 250 | 200 | 975 | 150 | 10 | 1.4625 | 1.4625 |  | 2.5675
27 | ST | 250 | 200 | 250 | 200 | 900 | 250 | 4 | 0.9 | 0.9 |  | 1.3328
28 | D/E | 300 | 350 |  |  | 650 | 0 | 10 | 1.05 | 1.05 |  | 0.702
29 | ST | 250 | 200 | 250 | 200 | 900 | 300 | 6 | 1.62 | 1.62 |  | 2.2848
30 | RING | 200 |  |  |  | 628 | 150 | 10 | 0.942 | 0.942 |  | 0.942
31 | FLEXIBLE DUCT | 200 |  |  |  |  | 800 | 10 | [5 empty] | 8
IDU-4C
1 | ST | 800 | 300 | 800 | 300 | 2200 | 600 | 1 | 1.32 |  | 1.32 | 1.5764
2 | OFF | 800 | 300 | 800 | 300 | 2200 | 600 | 1 | 1.32 |  | 1.32 | 1.5764
3 | OFF | 800 | 300 | 800 | 300 | 2200 | 1125 | 1 | 2.475 |  | 2.475 | 2.7587
4 | ST | 800 | 300 | 800 | 300 | 2200 | 1120 | 1 | 2.464 |  | 2.464 | 2.7474
5 | TP | 800 | 300 | 800 | 250 | 2150 | 350 | 1 | 0.7525 |  | 0.7525 | 0.9909
6 | EL | 800 | 250 | 800 | 250 | 2100 | 1300 | 1 | 2.73 |  | 2.73 | 3.0128
7 | ST | 800 | 250 | 800 | 250 | 2100 | 1120 | 4 | 9.408 |  | 9.408 | 10.5018
8 | Y-EL-01 | 400 | 250 | 400 | 250 | 1300 | 475 | 1 | 0.6175 | 0.6175 |  | 0.7774
9 | Y-EL-02 | 400 | 250 | 400 | 250 | 1300 | 475 | 1 | 0.6175 | 0.6175 |  | 0.7774
10 | TP | 400 | 250 | 450 | 250 | 1350 | 475 | 1 | 0.64125 | 0.64125 |  | 0.80615
11 | ST | 450 | 250 | 450 | 250 | 1400 | 1120 | 1 | 1.568 | 1.568 |  | 1.7714
12 | Y-EL-01 | 225 | 250 | 225 | 250 | 950 | 400 | 1 | 0.38 | 0.38 |  | 0.501
13 | Y-EL-02 | 225 | 250 | 225 | 250 | 950 | 400 | 1 | 0.38 | 0.38 |  | 0.501
14 | TP | 225 | 250 | 300 | 250 | 1025 | 300 | 1 | 0.3075 | 0.3075 |  | 0.4308
15 | ST | 300 | 250 | 300 | 250 | 1100 | 1170 | 1 | 1.287 | 1.287 |  | 1.463
16 | D/E | 350 | 300 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
0
17 | TP | 225 | 250 | 300 | 250 | 1025 | 300 | 1 | 0.3075 | 0.3075 |  | 0.4308
18 | ST | 300 | 250 | 300 | 250 | 1100 | 665 | 1 | 0.7315 | 0.7315 |  | 0.88128
19 | D/E | 350 | 300 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
0
20 | TP | 400 | 250 | 450 | 250 | 1350 | 535 | 1 | 0.72225 | 0.72225 |  | 0.89027
21 | ST | 450 | 250 | 450 | 250 | 1400 | 1120 | 2 | 3.136 | 3.136 |  | 3.5429
22 | Y-EL-01 | 300 | 25 | 300 | 250 | 650 | 340 | 1 | 0.221 | 0.221 |  | 0.30888
23 | Y-EL-02 | 300 | 25 | 300 | 250 | 650 | 340 | 1 | 0.221 | 0.221 |  | 0.30888
24 | ST | 300 | 250 | 300 | 250 | 1100 | 870 | 1 | 0.957 | 0.957 |  | 1.1174
25 | D/E | 300 | 350 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
0
24 | ST | 300 | 250 | 300 | 250 | 1100 | 950 | 1 | 1.045 | 1.045 |  | 1.2096
25 | ST | 300 | 250 | 300 | 250 | 1100 | 1180 | 1 | 1.298 | 1.298 |  | 1.4746
26 | D/E | 300 | 350 |  |  | 650 |  | 1 | 0.105 | 0.105 |  | 0.105
27 | SHU-BR | 350 | 250 | 300 | 250 | 1150 | 345 | 1 | 0.39675 | 0.39675 |  | 0.53489
28 | ST | 300 | 250 | 300 | 250 | 1100 | 510 | 1 | 0.561 | 0.561 |  | 0.70272
29 | ST | 300 | 250 | 300 | 250 | 1100 | 1170 | 1 | 1.287 | 1.287 |  | 1.463
30 | D/E | 350 | 300 |  |  | 650 | 0 | 1 | 0.105 | 0.105 |  | 0.105
31 | SHU-COL | 325 | 200 | 250 | 200 | 975 | 150 | 10 | 1.4625 | 1.4625 |  | 2.5675
32 | ST | 250 | 200 | 250 | 200 | 900 | 1020 | 2 | 1.836 | 1.836 |  | 2.1325
33 | D/E | 300 | 250 |  |  | 550 | 0 | 10 | 0.75 | 0.75 |  | 0.602
34 | ST | 250 | 200 | 250 | 200 | 900 | 300 | 8 | 2.16 | 2.16 |  | 3.0464
35 | RING | 200 |  |  |  | 628 | 150 | 10 | 0.942 | 0.942 |  | 0.942
36 | FLEXIBLE DUCT | 200 |  |  |  |  | 800 | 10 | [5 empty] | 8
RETURN AIR
1 | RAD-01 | 480 | 280 | 480 | 280 | 1520 | 500 | 1 | 0.76 | 0.76 |  | 0.76
2 | RAD-02 | 900 | 280 | 900 | 280 | 2360 | 650 | 1 | 1.534 | 1.534 |  | 1.534
TOTAL | [8 empty] | 129.3735 | 72.3326 | 57.0408 | 152.5106 | 0 | 24 | 0
[9 empty] | SQMTR | SQMTR | SQMTR | SQMTR | SQMTR | RMT | RMT

## SQUASH COURT (hidden)
TEAMONE HVAC SERVICES PVT. LTD.
DUCTING MEASUREMENT
PROJECT NAME : OBEROI ETERNIA - MULUND ( CLUBHOUSE )
Sr. No. | Description | Width | Height | Width | Height | Perimeter | Length | Qty | Area (Sq.Mtr.) | Ducting |  | Thermal Insulation | Accoustic Insulation | Flexible Duct | Canvas Connection | Remarks
[10 empty] | 24 G | 22 G
SQUASH COURT
IDU-5
1 | CANVAS | 1190 | 385 | 1190 | 385 | 3150 |  | 1 | [6 empty] | 3.15
2 | CON | 1190 | 385 | 700 | 330 | 2605 | 670 | 1 | 1.7453 |  | 1.7453 |  | 1.7453
3 | OFF | 700 | 350 | 700 | 350 | 2100 | 600 | 1 | 1.26 | 1.26 |  |  | 1.26
4 | ST | 700 | 350 | 700 | 350 | 2100 | 1120 | 1 | 2.352 | 2.352 |  | 2.4102
5 | TA | 700 | 350 | 450 | 350 | 1850 | 375 | 1 | 0.69375 | 0.69375 |  | 0.71325
6 | ST | 450 | 350 | 450 | 350 | 1600 | 1120 | 1 | 1.792 | 1.792 |  | 1.8502
7 | ST | 450 | 350 | 450 | 350 | 1600 | 1170 | 1 | 1.872 | 1.872 |  | 1.9328
8 | D/E | 450 | 350 |  |  | 800 |  | 1 | 0.1575 | 0.1575 |  | 0.1575
IDU-6
1 | CANVAS | 1190 | 385 | 1190 | 385 | 3150 |  | 1 | [6 empty] | 3.15
2 | CON | 1190 | 385 | 700 | 330 | 2605 | 670 | 1 | 1.7453 |  | 1.7453 |  | 1.7453
3 | OFF | 700 | 350 | 700 | 350 | 2100 | 600 | 1 | 1.26 | 1.26 |  |  | 1.26
4 | ST | 700 | 350 | 700 | 350 | 2100 | 1120 | 1 | 2.352 | 2.352 |  | 2.4102
5 | TA | 700 | 350 | 450 | 350 | 1850 | 335 | 1 | 0.61975 | 0.61975 |  | 0.63717
6 | ST | 450 | 350 | 450 | 350 | 1600 | 973 | 1 | 1.5568 | 1.5568 |  | 1.6074
7 | ST | 450 | 350 | 450 | 350 | 1600 | 1170 | 1 | 1.872 | 1.872 |  | 1.9328
8 | D/E | 450 | 350 |  |  | 800 |  | 1 | 0.1575 | 0.1575 |  | 0.1575
TOTAL | [8 empty] | 19.436 | 15.9453 | 3.4907 | 13.8092 | 6.0107 | 0 | 6.3
[9 empty] | SQMTR | SQMTR | SQMTR | SQMTR | SQMTR | RMT | RMT

## VCD (hidden)
TEAMONE HVAC SERVICES PVT. LTD.
MEASUREMENT SHEET
PROJECT NAME : OBEROI ETERNIA - MULUND ( CLUBHOUSE )
VOLUME CONTROL DAMPER
SR. NO. | LOCATION | DAMPER WIDTH | DAMPER HEIGHT | UNIT | AREA | QTY. | TOTAL AREA | GRAND TOTAL (IN SQ.MTR.)
|  | ( MM ) | ( MM )
1 | DAY CARE | 600 | 250 | SQ.MT | 0.15 | 1 | 0.15 | 1.9125
2 | DAY CARE | 700 | 250 | SQ.MT | 0.175 | 1 | 0.175
3 | CAFÉ | 700 | 300 | SQ.MT | 0.21 | 2 | 0.42
4 | CAFÉ | 500 | 250 | SQ.MT | 0.125 | 1 | 0.125
5 | CAFÉ | 250 | 250 | SQ.MT | 0.0625 | 3 | 0.1875
6 | GYM IDU 4A | 300 | 250 | SQ.MT | 0.075 | 1 | 0.075
7 | GYM | 450 | 250 | SQ.MT | 0.1125 | 2 | 0.225
8 | GYM IDU 4B | 350 | 300 | SQ.MT | 0.105 | 1 | 0.105
9 | GYM | 500 | 300 | SQ.MT | 0.15 | 1 | 0.15
10 | GYM IDU 4C | 300 | 250 | SQ.MT | 0.075 | 1 | 0.075
11 | GYM | 450 | 250 | SQ.MT | 0.1125 | 2 | 0.225
NON-RETURN DAMPER
1 | CAFÉ | 700 | 350 | SQ.MT | 0.245 | 2 | 0.49 | 0.49

## PLENUM (hidden)
TEAMONE HVAC SERVICES PVT. LTD.
MEASUREMENT SHEET
PROJECT NAME : OBEROI ETERNIA - MULUND ( CLUBHOUSE )
SUPPLY AIR PLENUM
SR. NO. | LOCATION | PLENUM LENGTH | PLENUM WIDTH | UNIT | QTY. | TOTAL QTY
1 | GYM AREA | 1000 | 100 | NOS. | 15 | 15 | Work Order Sizes differes from Execution Size
2 | CAFÉ | 900 | 100 | NOS. | 18 | 31
3 | DAY CARE | 900 | 100 | NOS. | 9
4 | SQUASH COURT 1 & 2 | 900 | 100 | NOS. | 4