## Tower - A
Measurments for Providing & installation fire proofing for MEP penetrations in Master Common Area:
Contractor Name | Falcon Acoustics & Passive fire solutions pvt. Ltd
Company Name | Oberoi Constructions Limited
Project Name | Oberoi Eternia
Scope of Work | Fire Sealant application for MEP penetrations on mca
Tower A Incharge | Avinash Sagare
| Eternia | Level - 36 / WIR REF. NO - 7307 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 3 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 2 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 37 / WIR REF. NO - 7691 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 2 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 38 / WIR REF.NO - 7385 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 9 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 2 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 39 / WIR REF.NO - 7386 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 2 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 40 / WIR REF.NO - 7387 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 41 / WIR REF.NO - 7388 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 2 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 42 / WIR REF.NO - 7389 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 6 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 5 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 43 / WIR REF.NO - 7690 |  |  | Tower - A | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
Fire Sealant Incharge (Signature) Tower A representative (Signature)

## Tower B
Measurments for Providing & installation fire proofing for MEP penetrations in Master Common Area:
Contractor Name | Falcon Acoustics & Passive fire solutions pvt. Ltd
Company Name | Oberoi Constructions Limited
Project Name | Oberoi Eternia
Scope of Work | Fire Sealant application for MEP penetrations on mca
Tower A Incharge | Avinash Sagare
| Eternia | Level - 31 / WIR REF.NO - 8228 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 32 / WIR REF.NO - 8230 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 33 / WIR REF.NO - 8231 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 9 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 34 / WIR REF.NO - 8232 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 9 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 35 / WIR REF.NO - 8234 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 36 / WIR REF.NO - 8235 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 37 / WIR REF.NO - 8236 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 38 / WIR REF.NO - 8237 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 6 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 5 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 39 / WIR REF.NO - 8238 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 5 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 40 / WIR REF.NO - 8239 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 5 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 41 / WIR REF.NO - 8240 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 42 / WIR REF.NO - 8241 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 6 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 43 / WIR REF.NO - 8242 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 44 / WIR REF.NO - 8243 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
` | Eternia | Level - 45 / WIR REF.NO - 8246 |  |  | Tower - B | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC |  | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE |  | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE |  | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS |  | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE |  | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
Fire Sealant Incharge (Signature) Tower B representative (signature)

## Tower C
Measurments for Providing & installation fire proofing for MEP penetrations in Master Common Area:
Contractor Name | Falcon Acoustics & Passive fire solutions pvt. Ltd
Company Name | Oberoi Constructions Limited
Project Name | Oberoi Eternia
Scope of Work | Fire Sealant application for MEP penetrations on mca
Tower C Incharge | Nilesh Sharma
| Eternia | Level - 40 / WIR REF. NO - 8933 |  |  | Tower - C | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 3 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 1 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE |  | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 41 / WIR REF. NO - 8934 |  |  | Tower - C | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 1 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE |  | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 4 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 42 / WIR REF.NO - 8935 |  |  | Tower - C | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 4 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
Fire Sealant Incharge (Signature) Tower A representative (Signature)

## Tower D
Measurments for Providing & installation fire proofing for MEP penetrations in Master Common Area:
Contractor Name | Falcon Acoustics & Passive fire solutions pvt. Ltd
Company Name | Oberoi Constructions Limited
Project Name | Oberoi Eternia
Scope of Work | Fire Sealant application for MEP penetrations on mca
Tower D Incharge | Nilesh Sharma
| Eternia | Level - 31 / WIR REF. NO - 9126 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 6 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 32 / WIR REF. NO - 9125 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 6 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 2 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 33 / WIR REF.NO - 9124 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 14 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 34 / WIR REF.NO - 8931 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 5 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 35 / WIR REF.NO - 8930 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 5 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 36 / WIR REF.NO - 8929 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 37 / WIR REF.NO - 8928 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 9 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 38 / WIR REF.NO - 8927 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 7 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS |  | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE |  | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 39 / WIR REF.NO - 8926 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 5 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 40 / WIR REF.NO - 8925 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 5 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE |  | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 41 / WIR REF.NO - 8924 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 13 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 5 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
| Eternia | Level - 42 / WIR REF.NO - 8923 |  |  | Tower - D | Date:
sc.no | Core Cut Dia (MM) | Penetrant Dia (MM) | Penetrant Depth (MM) | Penetrant type | nos | BOQ Reference | Sides Applied
1 | 50 | 32 | 200 | RCC Core & PVC | 18 | A | BOTH
2 | 50 | 12 | 100 | RCC Core & FRLS | 1 | B | BOTH
3 | 80 | 50 | 200 | RCC Core & GI PIPE | 4 | C | BOTH
4 | 80 | 65 | 200 | RCC Core & GI PIPE | 2 | D | BOTH
5 | 150 | 80 | 200 | RCC Core & FRLS | 1 | F | BOTH
6 | 150 | 75 | 200 | RCC Core & PVC PIPE | 1 | G | BOTH
7 | 75 | 50 | 425 | RCC Core & GI PIPE | 6 | H | BOTH
8 | 50 | 12 | 425 | RCC Core & FRLS | 6 | I | BOTH
9 | 100 | 80 | 230 | RCC Core & GI PIPE | 1 | J | BOTH
Fire Sealant Incharge (Signature) Tower A representative (Signature)